## Stories
| Story | Total Points | Total Hours | Hours Spent | Finished
Iteration 1 | House Set Up | 16 | 57 |  | 1 |  | Velocity | 18
| Entering Location | 4 | 12
| Efficiency | 4 | 13
| Custom Tariffs | 1 | 3 |  | 1
Stories Done | Hours of Sunlight | 2 | 8
| Old Panels | 1 | 4 |  | 1
Iteration 2 | List of Options | 4 | 10 |  | 1 |  | Velocity
| Power Generation | 4 | 20 |  | 1
| Yearly Profit | 2 | 8 |  | 1
| Time Till Profit Break Even | 2 | 8 |  |  | Previous Stories Finished
| Existing Profit | 2 | 8 |  | 1 | 3
| Create Scenario | 4 | 11 |  | 1
Stories Done | Edit Scenario | 1 | 5 |  | 1
| Delete Scenario | 1 | 2 |  | 1
Iteration 3 | Power Break Even Analysis | 4 | 13
| Maximum Cost | 2 | 3
| Email Results | 4 | 10
Stories Done | Save Entry | 2 | 4
| Chart for Displaying Results | 8 | 18
Iteration 4 | Logo/App Image | 4 | 16
| Different Tariffs | 2 | 6
| Save Tariffs | 2 | 6
| Automatic Locator | 2 | 6.5
Stories Done | Multiple Houses | 2 | 7
| Help Tips and Buttons | 2 | 22

## James
| 2012-08-21 | 2012-08-22 | 2012-09-23 | 2012-09-24 | 2012-08-25 | 2012-08-26 | 2012-08-27 | 2012-08-28 | 2012-08-29 | 2012-08-30 | 2012-08-31 | 2012-09-01 | 2012-09-02 | 2012-09-03 | Total Hours
House Set Up | [12 empty] | 4
Entering Location
Efficiency |  |  |  |  | 2 | 2 |  |  |  | 2 |  | 2 |  | 2
Custom Tariffs | [9 empty] | 1
Hours of Sunlight | [11 empty] | 1
Old Panels | [11 empty] | 2 |  | 2
Project Workload
Iteration Workload
| 2012-09-04 | 2012-09-05 | 2012-09-06 | 2012-09-07 | 2012-09-08 | 2012-09-09 | 2012-09-10 | 2012-09-11 | 2012-09-12 | 2012-09-13 | 2012-09-14 | 2012-09-15 | 2012-09-16 | 2012-09-17 | Total Hours
List of Options
Power Generation | 2012-09-11: 2; 2012-09-13: 4; 2012-09-16: 2
Yearly Profit | 2012-09-13: 2; 2012-09-15: 2; 2012-09-16: 4
Time Till Profit Break Even | 2012-09-17: 4
Existing Profit | 2012-09-15: 4; 2012-09-16: 2
Create Scenario
Edit Scenario
Delete Scenario
Project Workload
Iteration Workload
| 2012-09-25 | 2012-09-26 | 2012-09-27 | 2012-09-28 | 2012-09-29 | 2012-09-30 | 2012-10-01 | 2012-10-02 | 2012-10-03 | 2012-10-04 | 2012-10-05 | 2012-10-06 | 2012-10-07 | 2012-10-08 | Total Hours
Power Break Even Analysis
Maximum Cost
Email Results
Save Entry
Chart for Displaying Results
Project Workload
Iteration Workload
| 2012-10-09 | 2012-10-10 | 2012-10-11 | 2012-10-12 | 2012-10-13 | 2012-10-14 | 2012-10-15 | 2012-10-16 | 2012-10-17 | 2012-10-18 | 2012-10-19 | 2012-10-20 | 2012-10-21 | 2012-10-22 | Total Hours
Logo/App Image
Different Tariffs
Save Tariffs
Automatic Locator
Multiple Houses
Help Tips and Buttons
Project Workload
Iteration Workload
167
Note on A1: Enter the number of hours you have worked on the stories on the specified date

## Morgan
| 2012-08-21 | 2012-08-22 | 2012-09-23 | 2012-09-24 | 2012-08-25 | 2012-08-26 | 2012-08-27 | 2012-08-28 | 2012-08-29 | 2012-08-30 | 2012-08-31 | 2012-09-01 | 2012-09-02 | 2012-09-03 | Total Hours
House Set Up |  |  |  |  | 8.5 | 7.5 |  |  |  | 3 | 3.5 | 6 | 8 | 7.5
Entering Location | [10 empty] | 3.5
Efficiency
Custom Tariffs | [9 empty] | 4.5
Hours of Sunlight
Old Panels
| 2012-09-04 | 2012-09-05 | 2012-09-06 | 2012-09-07 | 2012-09-08 | 2012-09-09 | 2012-09-10 | 2012-09-11 | 2012-09-12 | 2012-09-13 | 2012-09-14 | 2012-09-15 | 2012-09-16 | 2012-09-17 | Total Hours
List of Options | 2012-09-09: 9.5
Power Generation
Yearly Profit
Time Till Profit Break Even
Existing Profit
Create Scenario | 2012-09-13: 9
Edit Scenario | 2012-09-14: 7
Delete Scenario | 2012-09-15: 4
| 2012-09-25 | 2012-09-26 | 2012-09-27 | 2012-09-28 | 2012-09-29 | 2012-09-30 | 2012-10-01 | 2012-10-02 | 2012-10-03 | 2012-10-04 | 2012-10-05 | 2012-10-06 | 2012-10-07 | 2012-10-08 | Total Hours
Power Break Even Analysis
Maximum Cost
Email Results
Save Entry
Chart for Displaying Results
| 2012-10-09 | 2012-10-10 | 2012-10-11 | 2012-10-12 | 2012-10-13 | 2012-10-14 | 2012-10-15 | 2012-10-16 | 2012-10-17 | 2012-10-18 | 2012-10-19 | 2012-10-20 | 2012-10-21 | 2012-10-22 | Total Hours
Logo/App Image
Different Tariffs
Save Tariffs
Automatic Locator
Multiple Houses
Help Tips and Buttons
Note on A1: Enter the number of hours you have worked on the stories on the specified date

## Tyrone
| 2012-08-21 | 2012-08-22 | 2012-09-23 | 2012-09-24 | 2012-08-25 | 2012-08-26 | 2012-08-27 | 2012-08-28 | 2012-08-29 | 2012-08-30 | 2012-08-31 | 2012-09-01 | 2012-09-02 | 2012-09-03 | Total Hours
House Set Up
Entering Location | [5 empty] | 2 | 3 | [5 empty] | 2 | 4
Efficiency | [6 empty] | 1 | [5 empty] | 1
Custom Tariffs
Hours of Sunlight | [7 empty] | 1 | 1 |  |  |  |  | 1
Old Panels
| 2012-09-04 | 2012-09-05 | 2012-09-06 | 2012-09-07 | 2012-09-08 | 2012-09-09 | 2012-09-10 | 2012-09-11 | 2012-09-12 | 2012-09-13 | 2012-09-14 | 2012-09-15 | 2012-09-16 | 2012-09-17 | Total Hours
List of Options
Power Generation | 2012-09-12: 1; 2012-09-13: 2; 2012-09-15: 6; 2012-09-16: 4; 2012-09-17: 13
Yearly Profit
Time Till Profit Break Even
Existing Profit
Create Scenario
Edit Scenario
Delete Scenario
| 2012-09-25 | 2012-09-26 | 2012-09-27 | 2012-09-28 | 2012-09-29 | 2012-09-30 | 2012-10-01 | 2012-10-02 | 2012-10-03 | 2012-10-04 | 2012-10-05 | 2012-10-06 | 2012-10-07 | 2012-10-08 | Total Hours
Power Break Even Analysis
Maximum Cost
Email Results
Save Entry
Chart for Displaying Results
| 2012-10-09 | 2012-10-10 | 2012-10-11 | 2012-10-12 | 2012-10-13 | 2012-10-14 | 2012-10-15 | 2012-10-16 | 2012-10-17 | 2012-10-18 | 2012-10-19 | 2012-10-20 | 2012-10-21 | 2012-10-22 | Total Hours
Logo/App Image
Different Tariffs
Save Tariffs
Automatic Locator
Multiple Houses
Help Tips and Buttons
Note on A1: Enter the number of hours you have worked on the stories on the specified date

## Oscar
| 2012-08-21 | 2012-08-22 | 2012-09-23 | 2012-09-24 | 2012-08-25 | 2012-08-26 | 2012-08-27 | 2012-08-28 | 2012-08-29 | 2012-08-30 | 2012-08-31 | 2012-09-01 | 2012-09-02 | 2012-09-03 | Total Hours
House Set Up |  |  |  | 2 | 1 | [6 empty] | 3 | 7 | 10
Entering Location | [11 empty] | 1 | 3
Efficiency
Custom Tariffs
Hours of Sunlight
Old Panels
| 2012-09-04 | 2012-09-05 | 2012-09-06 | 2012-09-07 | 2012-09-08 | 2012-09-09 | 2012-09-10 | 2012-09-11 | 2012-09-12 | 2012-09-13 | 2012-09-14 | 2012-09-15 | 2012-09-16 | 2012-09-17 | Total Hours
List of Options | 2012-09-09: 1.5; 2012-09-10: 2
Power Generation
Yearly Profit
Time Till Profit Break Even
Existing Profit
Create Scenario | 2012-09-10: 2; 2012-09-14: 2; 2012-09-15: 5; 2012-09-16: 2; 2012-09-17: 7
Edit Scenario | 2012-09-14: 2; 2012-09-15: 1; 2012-09-16: 5
Delete Scenario | 2012-09-14: 2; 2012-09-17: 2
| 2012-09-25 | 2012-09-26 | 2012-09-27 | 2012-09-28 | 2012-09-29 | 2012-09-30 | 2012-10-01 | 2012-10-02 | 2012-10-03 | 2012-10-04 | 2012-10-05 | 2012-10-06 | 2012-10-07 | 2012-10-08 | Total Hours
Power Break Even Analysis
Maximum Cost
Email Results
Save Entry
Chart for Displaying Results
| 2012-10-09 | 2012-10-10 | 2012-10-11 | 2012-10-12 | 2012-10-13 | 2012-10-14 | 2012-10-15 | 2012-10-16 | 2012-10-17 | 2012-10-18 | 2012-10-19 | 2012-10-20 | 2012-10-21 | 2012-10-22 | Total Hours
Logo/App Image
Different Tariffs
Save Tariffs
Automatic Locator
Multiple Houses
Help Tips and Buttons
Note on A1: Enter the number of hours you have worked on the stories on the specified date