## Stories
| Story | Total Points | Total Hours | Hours Spent | Finished
Iteration 1 | House Set Up | 16 | 57 | 71 | 1 | Velocity | 18
| Entering Location | 4 | 12 | 18.5 | 1
| Efficiency | 4 | 13 | 12 | 1
| Custom Tariffs | 1 | 3 | 5.5 | 1
Stories Done | Hours of Sunlight | 2 | 8 | 4
5 | Old Panels | 1 | 4 | 4 | 1
Iteration 2 | List of Options | 4 | 10 | 13 | 1 | Velocity | 18
| Power Generation | 4 | 20 | 34 | 1
| Yearly Profit | 2 | 8 | 8 | 1
| Time Till Profit Break Even | 2 | 8 | 4
| Existing Profit | 2 | 8 | 6 | 1
| Create Scenario | 4 | 11 | 27 | 1
Stories Done | Edit Scenario | 1 | 5 | 15 | 1
7 | Delete Scenario | 1 | 2 | 8 | 1
Iteration 3 | Power Break Even Analysis | 4 | 13 | 5 | 1 | Velocity | 15
| Maximum Cost | 2 | 3 | 0 | 1
| Email Results | 4 | 10 | 6
Stories Done | Save Entry | 2 | 4 | 17 | 1
4 | Time Till Profit Break Even | 2 | 8 | 13 | 1
Iteration 4 | Logo/App Image | 4 | 6 | 3 | 1
| Different Tariffs | 2 | 6 | 10 | 1
| Save Tariffs | 2 | 6 | 6 | 1
Stories Done | Email Results | 4 | 10 | 4 | 1
5 | Help Tips and Buttons | 2 | 6 | 5 | 1
|  | 76 | 241

## James
Iteration 1 Ideal burndown | 241 | 233.54 | 226.08 | 218.62 | 211.16 | 203.7 | 196.24 | 188.78 | 181.32 | 173.86 | 166.4 | 158.94 | 151.48 | 144.02
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
House Set Up | Day 13: 4 | 4
Entering Location | [14 empty] | 0
Efficiency | Day 5: 2; Day 6: 2; Day 10: 2; Day 12: 2; Day 14: 2 | 10
Custom Tariffs | [14 empty] | 1 | bar: Day 10
Hours of Sunlight | [14 empty] | 1 | bar: Day 12
Old Panels | Day 12: 2; Day 14: 2 | 4
Project Workload | 241 | 241 | 241 | 239 | 227.5 | 216 | 212 | 211 | 210 | 199.5 | 192.5 | 177.5 | 152.5 | 147
Iteration Workload | 97 | 97 | 97 | 95 | 83.5 | 72 | 68 | 67 | 66 | 55.5 | 48.5 | 33.5 | 8.5 | 3
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
List of Options | [14 empty] | 0
Power Generation | Day 8: 2; Day 10: 4; Day 13: 2 | 8
Yearly Profit | Day 10: 2; Day 12: 2; Day 13: 4 | 8
Time Till Profit Break Even | Day 14: 4 | 4
Existing Profit | Day 12: 4; Day 13: 2 | 6
Create Scenario | [14 empty] | 0
Edit Scenario | [14 empty] | 0
Delete Scenario | [14 empty] | 0
Project Workload | 147 | 147 | 147 | 147 | 147 | 136 | 132 | 130 | 129 | 112 | 99 | 77 | 75 | 75
Iteration Workload | 72 | 72 | 72 | 72 | 72 | 61 | 57 | 55 | 54 | 37 | 24 | 2 | 0 | 0
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
Power Break Even Analysis | Day 8: 2; Day 10: 2 | 4
Maximum Cost | [14 empty] | 0
Email Results | [14 empty] | 0
Save Entry | [14 empty] | 0
Time Till Profit Break Even | Day 12: 4; Day 13: 2 | 6
Project Workload | 75 | 75 | 70 | 70 | 70 | 65 | 61 | 59 | 59 | 57 | 57 | 50 | 41 | 34
Iteration Workload | 38 | 38 | 33 | 33 | 33 | 28 | 24 | 22 | 22 | 20 | 20 | 13 | 4 | -3
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
Logo/App Image | [14 empty] | 0
Different Tariffs | Day 6: 1; Day 7: 2 | 3
Save Tariffs | [14 empty] | 0
Automatic Locator | [14 empty] | 0
Email Results | [14 empty] | 0
Help Tips and Buttons | [14 empty] | 0
Project Workload | 34 | 31 | 31 | 26 | 26 | 21 | 18 | 18 | 18 | 18 | 17 | 15 | 5 | 5
Iteration Workload | 34 | 31 | 31 | 26 | 26 | 21 | 18 | 18 | 18 | 18 | 17 | 15 | 5 | 5
Iteration 2 Ideal Burndown | 147 | 141.3 | 135.6 | 129.9 | 124.2 | 118.5 | 112.8 | 107.1 | 101.4 | 95.7 | 90 | 84.3 | 78.6 | 74.3
Iteration 3 Ideal Burndown | 75 | 72.1 | 69.2 | 66.3 | 63.4 | 60.5 | 57.6 | 54.7 | 51.8 | 48.9 | 46 | 43.1 | 40.2 | 37.3
Iteration 4 Ideal Burndown | 38 | 35.0769 | 32.1538 | 29.2308 | 26.3077 | 23.3846 | 20.4615 | 17.5385 | 14.6154 | 11.6923 | 8.7692 | 5.8462 | 2.9231 | 0

## Morgan
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
House Set Up | Day 5: 8.5; Day 6: 7.5; Day 10: 3; Day 11: 3.5; Day 12: 6; Day 13: 8; Day 14: 7.5 | 44
Entering Location | Day 11: 3.5 | 3.5
Efficiency | [14 empty] | 0
Custom Tariffs | Day 10: 4.5 | 4.5
Hours of Sunlight | [14 empty] | 0
Old Panels | [14 empty] | 0
| 0 | 0 | 0 | 0 | 8.5 | 7.5 | 7.5 | 20.5 | 0 | 7.5 | 14.5 | 6 | 8 | 7.5
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
List of Options | Day 6: 9.5 | 9.5
Power Generation | [14 empty] | 0
Yearly Profit | [14 empty] | 0
Time Till Profit Break Even | [14 empty] | 0
Existing Profit | [14 empty] | 0
Create Scenario | Day 10: 9 | 9
Edit Scenario | Day 11: 7 | 7
Delete Scenario | Day 12: 4 | 4
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
Power Break Even Analysis | [14 empty] | 0
Maximum Cost | [14 empty] | 0
Email Results | Day 6: 3; 4 Day 12: 3 | 6
Save Entry | Day 3: 5; 4 Day 13: 2; 4 Day 14: 1 | 8
Time Till Profit Break Even | [14 empty] | 0
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
Logo/App Image | Day 2: 3 | 3
Different Tariffs | Day 6: 4 | 4
Save Tariffs | [14 empty] | 1 | bar: Day 7
Automatic Locator | [14 empty] | 1 | bar: Day 11
Email Results | Day 13: 4 | 4
Help Tips and Buttons | Day 4: 5 | 5

## Tyrone
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
House Set Up | [14 empty] | 0
Entering Location | Day 6: 2; Day 7: 3; Day 13: 2; Day 14: 4 | 11
Efficiency | [14 empty] | 2 | bar: Day 7; Day 13
Custom Tariffs | [14 empty] | 0
Hours of Sunlight | [14 empty] | 3 | bar: Day 8 to Day 9; Day 14
Old Panels | [14 empty] | 0
| 0 | 0 | 0 | 0 | 0 | 2 | 4 | 1 | 1 | 0 | 0 | 0 | 3 | 5
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
List of Options | [14 empty] | 0
Power Generation | Day 9: 1; Day 10: 2; Day 12: 6; Day 13: 4; Day 14: 13 | 26
Yearly Profit | [14 empty] | 0
Time Till Profit Break Even | [14 empty] | 0
Existing Profit | [14 empty] | 0
Create Scenario | [14 empty] | 0
Edit Scenario | [14 empty] | 0
Delete Scenario | [14 empty] | 0
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
Power Break Even Analysis | [14 empty] | 0
Maximum Cost | [14 empty] | 0
Email Results | [14 empty] | 0
Save Entry | [14 empty] | 0
Time Till Profit Break Even | [14 empty] | 0
Backend Development | Day 5: 6; Day 6: 4; Day 12: 3; Day 13: 5; Day 14: 1 | 19
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
Logo/App Image | [14 empty] | 0
Different Tariffs | 5 Day 13: 3 | 3
Save Tariffs | 3 Day 12: 2; 5 Day 13: 3 | 5
Automatic Locator | [14 empty] | 0
Email Results | [14 empty] | 0
Help Tips and Buttons | [14 empty] | 0
Backend Development | 6 Day 5: 3; 4 Day 6: 3; 4 Day 11: 2; 3 Day 12: 4 | 12

## Oscar
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
House Set Up | Day 4: 2; Day 5: 1; Day 12: 3; Day 13: 7; Day 14: 10 | 23
Entering Location | Day 12: 1; Day 13: 3 | 4
Efficiency | [14 empty] | 0
Custom Tariffs | [14 empty] | 0
Hours of Sunlight | [14 empty] | 0
Old Panels | [14 empty] | 0
| 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 10
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
List of Options | Day 6: 1.5; Day 7: 2 | 3.5
Power Generation | [14 empty] | 0
Yearly Profit | [14 empty] | 0
Time Till Profit Break Even | [14 empty] | 0
Existing Profit | [14 empty] | 0
Create Scenario | Day 7: 2; Day 11: 2; Day 12: 5; Day 13: 2; Day 14: 7 | 18
Edit Scenario | Day 11: 2; Day 12: 1; Day 13: 5 | 8
Delete Scenario | Day 11: 2; Day 14: 2 | 4
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
Power Break Even Analysis | [14 empty] | 1 | bar: 2 Day 14
Maximum Cost | [14 empty] | 0
Email Results | [14 empty] | 0
Save Entry | Day 6: 2; Day 7: 2; 2 Day 14: 5 | 9
Chart for Displaying Results | Day 7: 2; 2 Day 13: 5 | 7
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total Hours
Logo/App Image | [14 empty] | 0
Different Tariffs | [14 empty] | 0
Save Tariffs | [14 empty] | 0
Automatic Locator | [14 empty] | 0
Email Results | [14 empty] | 0
Help Tips and Buttons | [14 empty] | 0